HCG FOUNDATION: PROPOSAL FOR NIDAN DAAN - CANCER CARE DIAGNOSTICS SUPPORT INITIATIVE

PROJECT OVERVIEW:

| Project Name: | NIDAN DAAN |
| --- | --- |
| Project Title : | Cancer care Diagnostics Support |
| NGO Name | HCG Foundation |
| Contact Person | Mr. Feros Khan |
| Phone number | 9986929057 |
| Correspondence address | No. 3 Ground Floor, Tower Block, Unity Buildings Complex, Mission Road District: Bangalore, State Karnataka PIN: 560027 Phone number with S.T.D. code: 080 – 46607760 |
| Proposed location | Ranchi |
| Proposed Budget | 50 lakhs |
| Thematic Area | Healthcare |

- Organizational Profile:

| - Name of the organization (As per Registration) | HCG Foundation |
| --- | --- |
| - Registered Address | No. 3 ground floor ,Unity Building complex, mission road, Bangalore-560027 |
| - Correspondence Address | No. 3 ground floor ,Unity Building complex, mission road, Bangalore-560027 |
| - Website | https://www.hcgfoundation.org/ |
| - Contact Person | Mr. Feros Khan |
| - Mobile number | +91-9986929057 |
| - Email Address | feros@hcgel.com |

- Legal and Registration Status:

| - Date of registration | 04-12-2006 |  |
| --- | --- | --- |
| - Registration Type | Trust |  |
| - PAN | AAATH6254R |  |
| - TAN (if applicable) | BLRH03304A |  |
| - GST (if applicable) | NA |  |
| - Tax Exemption Certificate | 12A |  |
|  | 80G |  |
| - Acknowledgment of Income Tax return along with IT Return filled | To be attached/To be provided upon request |  |
| - CSR Registration Number | CSR00030677 |  |
| - Registration under FCRA 2010 | Date of Registration | 04-11-2023 |
|  | Registration number | 094421886 |
| - Darpan Registration | Date of Registration | 03-07-2018 |
|  | Registration number | KA/2017/0162762 |

- Details about Trustees of the organization:

| Name | Designation | Appointment date |
| --- | --- | --- |
| DR.B.S.AJAIKUMAR | Managing Trustee | 04.12.2006 |
| ANJALI AJAIKUMAR ROSSI | Trustee | 22.02.2021 |
| DR.GANESH NAYAK | Trustee | 04.12.2006 |
| DR.RAMESH S BILIMAGGA | Trustee | 22.02.2021 |
| SATHISH SHENOY | Trustee | 04.12.2006 |

- Previous Partners/Donor agencies of the organization:

- Merck Pharmaceuticals - ABB - CVC - Child Help Foundation - Child Vikas foundation - CVC Capital Partners - Prestige Group - Sarojini Damodaran - NES - Go colors

- Organizational Background: (Organization profile, vision & mission, work profile, locations the organization works at and key areas of impact and area of operation of the organization):

HCG Foundation is a unique not-for-profit organization that raises funds through donations, grants, and CSR funds to help economically marginalized patients, raise awareness about cancer and its prevention, and conduct cancer early detection camps. HCG Foundation was constituted and registered as a Public Charitable Trust on 4th December 2006 with the single-minded aim of improving the quality of life of patients by empowering them to avail the best cancer care that medical science can offer. It has helped over 4,120 patients and conducted more than 482 awareness camps since its inception catering to 52,000 beneficiaries. Vision: - Ensuring access to quality cancer treatment for those in need and creating awareness on Cancer and its Prevention Mission: - - Provide financial support to those who cannot afford cancer treatment. - Spread awareness on cancer and cure. - Make early detection service more accessible for rural communities. - Educate on healthy lifestyle habits and prevention of cancer. - Provide psychological support to the family of cancer affected. - Sponsor, promote and conduct research activities towards prevention, treatment and eradication of cancer.

- Awards and Recognition (if any)

- Awarded to HCG Foundation: Bengaluru NGO’s Leadership Award 2017 - Certificate of Merit Awarded to HCG Foundation: National CSR Leadership Certificate of merit 2016.

Section 2: Project Proposal

- Project Identification details-

| - Project Name | NIDAN DAAN - CANCER CARE DIAGNOSTICS SUPPORT INITIATIVE |
| --- | --- |
| - Thematic Pillar | Health (Cancer Care) |
| - Proposed Location(City/Village & State) | Ranchi – Jharkhand |
| - Total Proposed Beneficiary Reach | 320 |
| - Total Proposed Budget | 50 lakhs |

2.Proposal Abstract:

The HCG Foundation proposes a Diagnostic Support Initiative in Ranchi, Jharkhand, to assist economically disadvantaged cancer patients who are eligible for treatment under the Central Government Health Scheme (CGHS). Although CGHS covers the cost of cancer treatment, it does not include the crucial diagnostic tests required prior to therapy initiation. This gap often leaves financially vulnerable patients unable to complete their diagnostic work-up, resulting in treatment delays or discontinuation. Through this project, the Foundation will provide a subsidized diagnostic package at ₹15,000 per patient, which includes PT-INR, Viral Markers, CBC, Serum Creatinine, CT Scan with Contrast, and Biopsy — all essential investigations for confirming diagnosis and assessing treatment fitness. Additionally, PET CT scans will be offered at a reduced cost of ₹12,000 for clinically indicated cases. The total project cost of ₹50 lakhs will enable approximately 240 patients to receive comprehensive diagnostic testing and 80 patients to undergo PET CT scans. By removing financial barriers to these critical tests, the project will ensure that low-income and socially vulnerable patients can proceed to CGHS-funded treatment without interruption, completing their cancer care continuum with dignity and hope. This initiative reflects the HCG Foundation’s commitment to making high-quality cancer diagnosis and treatment accessible, affordable, and equitable for all segments of society.

3. Background /Rationale of the Project:

Cancer continues to pose a major public health challenge in India, with diagnosis and treatment often hindered by financial constraints and limited access to essential diagnostic facilities. In Ranchi, while the Central Government Health Scheme (CGHS) supports the cost of cancer treatment, it does not cover key pre-treatment diagnostic investigations such as PT-INR, Viral Markers, CBC, Serum Creatinine, CT Scan with Contrast, and Biopsy. These tests are essential for confirming the diagnosis, assessing patient fitness, and formulating an appropriate treatment plan. For many economically disadvantaged patients, the cost of these investigations becomes an insurmountable barrier. Without financial support, patients are often unable to complete the necessary diagnostic work-up, leading to delays in treatment initiation or even treatment discontinuation. Such delays can have severe implications on clinical outcomes and overall survival rates. To address this gap, the HCG Foundation, in collaboration with --, proposes a dedicated Diagnostic Support Initiative. Under this project, essential diagnostic tests will be conducted at HCG–Abdur Razzaque Ansari Cancer Hospital, a leading comprehensive cancer care center in the region equipped with advanced diagnostic and imaging facilities. The initiative aims to provide subsidized diagnostic services to low-income and financially vulnerable cancer patients, enabling them to complete their diagnostic evaluation and proceed to CGHS-supported treatment without financial hindrance. The project will also make PET CT scans available at a reduced cost for cases requiring further staging, ensuring a complete and accurate assessment of disease extent. By bridging the diagnostic gap, this project will help patients access timely, evidence-based treatment, improve adherence, and ultimately enhance treatment outcomes. More importantly, it will allow disadvantaged patients to complete their cancer care journey with dignity, reinforcing the HCG Foundation’s mission to make quality cancer care accessible and affordable for all. ### Importance of proposed Diagnostic Tests While the Central Government Health Scheme (CGHS) package in Ranchi provides comprehensive coverage for cancer treatment, it does not include the essential pre-treatment diagnostic investigations required to confirm disease, assess patient fitness, and plan the appropriate line of therapy. These tests are mandatory prerequisites before any surgical or medical intervention can begin. In the absence of diagnostic support, patients often face delays in diagnosis and treatment initiation, adversely impacting their prognosis. The diagnostic tests proposed under this initiative are therefore critical to safe, timely, and effective cancer care. Each investigation plays a unique and indispensable role: - PT-INR: Evaluates blood-clotting ability, ensuring surgical and procedural safety. - Viral Markers (HBsAg, HCV, HIV): Identifies coexisting viral infections that influence treatment protocols and infection control. - Complete Blood Count (CBC): Provides baseline data on hemoglobin, white cells, and platelets, essential for assessing patient fitness for therapy. - Serum Creatinine: Measures kidney function to ensure safe use of contrast agents and chemotherapy drugs. - CT Scan with Contrast: Offers detailed imaging for tumor localization, staging, and treatment planning. - Biopsy: Confirms the cancer diagnosis and histological subtype, forming the foundation for individualized treatment decisions.

4..Objectives of the Project

Objectives-

- To provide subsidized diagnostic support to approximately 240 economically (approximately 20 per month) disadvantaged cancer patients through a comprehensive diagnostic package (PT-INR, Viral Markers, CBC, Serum Creatinine, CT Scan with Contrast, and Biopsy) at a subsidized cost of ₹15,000 per patient. - To offer PET CT scans at a reduced rate of ₹12,000 for approximately 80 patients, ensuring accurate disease staging and treatment planning for cases requiring advanced imaging. - To bridge the diagnostic gap in CGHS coverage by supporting essential pre-treatment investigations that are not included in the CGHS package, thereby enabling smooth transition from diagnosis to treatment. - To ensure timely initiation and completion of treatment by eliminating diagnostic delays caused by financial constraints, thus improving overall treatment adherence and outcomes. - To strengthen equitable access to cancer diagnostics in Jharkhand by establishing a sustainable model of subsidized testing for low-income and socially vulnerable patients.

- Proposed Output/Outcome of the project:

- 240 economically disadvantaged patients will receive complete diagnostic evaluations. - 80 patients will undergo PET CT scans at a reduced rate for accurate disease staging. - Diagnostic delays for CGHS-supported patients will be significantly reduced. - Higher treatment completion rates among low-income cancer patients. - Strengthened access to affordable, high-quality diagnostic services in Jharkhand.

- Monitoring and Evaluation Plan

A structured reporting system will be implemented to ensure transparency and accountability throughout the Diagnostic Support Initiative at HCG–Abdur Razzaque Ansari Cancer Hospital, Irba, Ranchi. Monthly progress reports will document patient enrollment, diagnostics completed, PET CT scans, and fund utilization. Quarterly review reports will summarize cumulative achievements, financial updates, and patient feedback, while a mid-term review at six months will assess progress and recommend improvements. At the end of the 12-month project, an annual completion report will present consolidated outcomes, treatment linkage data, audited financial statements, and impact summaries. All reports will combine quantitative data with qualitative insights to provide a comprehensive, evidence-based account of the project’s performance and outcomes for submission to the HCG Foundation Board and donors.

- BUDGET DETAILS-

TOTAL Budget: 50 lakhs

.

Budget  details-

| Sr. No | Service | No. of patients | Unit Cost (₹) | Total Cost (₹) |
| --- | --- | --- | --- | --- |
| 1 | Diagnostic Package (Full)- PT-INR, Viral Markers, CBC, Serum Creatinine, CT Scan with Contrast, Biopsy | 240 | 15,000 | 36,00,000 |
| 2. | PET CT Scan- Optional add-on for staging, as per clinical need | 80 | 12,000 | 9,60,000 |
| Total cost for diagnostic tests |  |  |  | 45,60,000 |
| 3 | Administrative cost @4.8% |  |  | 2,40,000 |
| Total project cost |  |  |  | 50,00,000 |

DURATION OF THE PROJECT –

The proposed Diagnostic Support Initiative will be implemented over a 12-month period, commencing on 1st January 2026 to 31st December 2026. During this period, all key activities—including patient identification, diagnostic testing, PET CT scans for eligible cases, data collection, monitoring, and reporting—will be carried out at HCG–Abdur Razzaque Ansari Cancer Hospital, Irba, Ranchi. This one-year duration will allow sufficient time to achieve the project’s objectives and ensure measurable impact on improving diagnostic access and treatment completion among economically disadvantaged cancer patients.