HCG FOUNDATION: PROPOSAL FOR SHAKTI KAVAJ HPV VACCINATION OF ADOLESCENT                            GIRLS

PROJECT OVERVIEW:

| Project Name | Shakti Kavaj ( Shield of Strength) |
| --- | --- |
| Project Title | HPV vaccination for adolescent girls |
| Submitted to |  |
| NGO Name | HCG Foundation |
| Contact Person | Mr. Feros Khan |
| Phone number | 9986929057 |
| Correspondence address | No. 3 Ground Floor, Tower Block, Unity Buildings Complex, Mission Road District: Bangalore, State Karnataka PIN: 560027 Phone number with S.T.D. code: 080 – 46607760 |
| Proposed location | Pan India |
| Proposed Budget | 19,52,000 (Nineteen lakhs fifty-two thousand) |
| Thematic Area | Healthcare (Preventative healthcare) |

- Organizational Profile:

| - Name of the organization (As per Registration) | HCG Foundation |
| --- | --- |
| - Registered Address | No. 3 ground floor, Unity Building complex, mission road, Bangalore-560027 |
| - Correspondence Address | No. 3 ground floor, Unity Building complex, mission road, Bangalore-560027 |
| - Website | https://www.hcgfoundation.org/ |
| - Contact Person | Mr. Feros Khan |
| - Mobile number | +91-9986929057 |
| - Email Address | feros@hcgel.com |

- Legal and Registration Status:

| - Date of registration | 04-12-2006 |  |
| --- | --- | --- |
| - Registration Type | Trust |  |
| - PAN | AAATH6254R |  |
| - TAN (if applicable) | BLRH03304A |  |
| - GST (if applicable) | NA |  |
| - Tax Exemption Certificate | 12A |  |
|  | 80G |  |
| - Acknowledgment of Income Tax return along with IT Return filled | To be attached/To be provided upon request |  |
| - CSR Registration Number | CSR00030677 |  |
| - Registration under FCRA 2010 | Date of Registration | 04-11-2023 |
|  | Registration number | 094421886 |
| - Darpan Registration | Date of Registration | 03-07-2018 |
|  | Registration number | KA/2017/0162762 |

- Details about Trustees of the organization:

| Name | Designation | Appointment date |
| --- | --- | --- |
| DR.B.S. AJAIKUMAR | Managing Trustee | 04.12.2006 |
| ANJALI AJAIKUMAR ROSSI | Trustee | 22.02.2021 |
| DR. GANESH NAYAK | Trustee | 04.12.2006 |
| DR. RAMESH S BILIMAGGA | Trustee | 22.02.2021 |
| SATHISH SHENOY | Trustee | 04.12.2006 |

- Previous Partners/Donor agencies of the organization:

- Merck Pharmaceuticals - ABB - CVC - Child Help Foundation - Child Vikas foundation - CVC Capital Partners - Prestige Group - Sarojini Damodaran - NES - Go Fashion

- Organizational Background: (Organization profile, vision & mission, work profile, locations the organization works at and key areas of impact and area of operation of the organization):

HCG Foundation is a unique not-for-profit organization that raises funds through donations, grants, and CSR funds to help economically marginalized patients, raise awareness about cancer and its prevention, and conduct early cancer detection camps. HCG Foundation was constituted and registered as a Public Charitable Trust on 4th December 2006 with the single-minded aim of improving the quality of life of patients by empowering them to avail the best cancer care that medical science can offer. It has helped over 4,120 patients and conducted more than 482 awareness camps since its inception catering to 52,000 beneficiaries. Vision: - Ensuring access to quality cancer treatment for those in need and creating awareness on Cancer and its Prevention Mission: - - Provide financial support to those who cannot afford cancer treatment. - Spread awareness of cancer and cure. - Make early detection services more accessible for rural communities. - Educate on healthy lifestyle habits and prevent cancer. - Provide psychological support to the family of cancer affected. - Sponsor, promote and conduct research activities towards prevention, treatment and eradication of cancer.

- Awards and Recognition (if any)

- Awarded to HCG Foundation: Bengaluru NGO’s Leadership Award 2017 - Certificate of Merit Awarded to HCG Foundation: National CSR Leadership Certificate of Merit 2016.

Section 2: Project Proposal

- Project Identification details-

| - Project Name | Shakti Kavaj (Shield of Strength) |
| --- | --- |
| - Project Title | HPV vaccination for adolescent girls |
| - Thematic Pillar | Healthcare (Preventative Healthcare) |
| - Proposed Location (City/Village & State) | Pan India |
| - Total Proposed Beneficiary Reach | 200 |
| - Total Proposed Budget | 19,52,000 |

2.Proposal Abstract: (to be written in a max. 200 words)

Cervical cancer remains one of the most preventable yet deadliest diseases affecting women in India, which accounts for nearly 25% of the global burden. Persistent infection with high-risk types of Human Papillomavirus (HPV), particularly types 16 and 18 is responsible for the majority of these cases. Although effective vaccines exist, coverage among Indian adolescents remains dangerously low due to cost, lack of awareness, logistical barriers. To address this urgent public health need, the HCG Foundation proposes an HPV vaccination campaign targeting 200 underserved adolescents (girls aged 9-14 years). This 12-month (1st January 2026-31st December2026) initiative will deploy a community-and school-based model that integrates awareness generation, vaccine delivery, and health system strengthening. The campaign will also engage parents, teachers, and healthcare workers to build sustainable vaccine acceptance and public trust. By investing in prevention today, this project will save thousands of lives tomorrow and move India significantly closer to the goal of eliminating cervical cancer as a public health threat. The project seeks to vaccinate 200 girls, at the cost of ₹19,52,000 s to support vaccine procurement, immunization and awareness drives. Expected outcomes will include full vaccination of 200 adolescent girls, improved HPV knowledge among community members, and a replicable model to vaccinate adolescents in the community.

3. Background /Rationale of the Project:

Cervical cancer remains one of the leading causes of cancer-related deaths among women in India, despite it being a largely preventable disease. Globally, cervical cancer affects hundreds of thousands of women each year, and tragically, India bears a disproportionate share of this burden. The country accounts for nearly one-fourth of all global cervical cancer deaths. Each year, more than 123,000 women in India are diagnosed with the disease, and over 67,000 lose their lives. These statistics are especially heartbreaking given that cervical cancer is preventable, treatable, and even curable when detected early. The primary cause of cervical cancer is persistent infection with certain high-risk types of human papillomavirus (HPV), particularly types 16 and 18, which together account for approximately 70% of all cases. Decades of research have demonstrated the effectiveness of HPV vaccination in preventing these infections. When administered before the onset of sexual activity, HPV vaccines are 90-100% effective in protecting against infection by these high-risk virus types. In addition to vaccination, regular cervical screening plays a critical role in detecting precancerous changes preventing progression to cancer. Despite the overwhelming evidence in support of HPV vaccination and cervical screening, coverage in India remains alarmingly low. Less than 10% of eligible girls have received the HPV vaccine, far below the levels needed to achieve population-wide immunity. The reasons for this are multifaceted. There is a significant lack of awareness about the disease and the vaccine, both among the general population. Myths, stigma, and misinformation around vaccination further discourage uptake. In many regions, especially rural and underserved communities, logistical barriers such as cost, limited availability, and lack of trained healthcare workers exacerbate the problem. The consequences of this inaction are severe-not just in terms of human lives lost, but also in terms of economic impact, social disruption, and emotional suffering. Women in the most economically productive years of their lives are affected, often leaving behind families that depend on them. The loss is compounded by the fact that cervical cancer is one of the few cancers that is preventable with a vaccine. Investing in prevention through widespread HPV vaccination and community-based education campaigns offers a cost-effective sustainable and humane solution. By raising awareness, improving access and subsidizing vaccination costs, we can significantly reduce the incidence and mortality of cervical cancer in India. This project aims to address these critical gaps through targeted outreach, community mobilization, school-based vaccine drives, and partnerships with local health systems. The goal is clear: no woman should die of a disease that we have the tools to prevent. With the right support and funding, we can move towards a future where cervical cancer is a rarity, not a tragedy. The time to act is now, before more lives are unnecessarily lost in this preventable disease.

4. Theory of Change:

5.Objectives of the Project (Overall and Specific):

| Objective | Strategy to achieve the objective |
| --- | --- |
| - Increased HPV vaccine coverage among girls aged 9-14 in underserved communities. | Partner with government, low-income private and charitable schools to organize vaccination camps. |
| - Raise awareness and acceptance of HPV vaccination and cervical cancer prevention among adolescents, parents, teachers and community leaders. | Conduct awareness workshops in schools, orphanages and community centers. Use posters, educational pamphlets and videos for awareness generation in local languages. |
| - Establish a reliable system for monitoring, evaluation, and learning to inform scale-up. | Develop and maintain data to share progress with donors and other stakeholders. |

- Activities proposed during the Project-

| Phase number | List of activities proposed during the phase |
| --- | --- |
| Phase 1: Stakeholder consultation and partnership building. | Reach out to government schools, NGOs, and orphanages. Sign agreements with schools. Identify HPV vaccine vendors as per the procurement policy of the foundation. |
| Phase 2: Mapping, Program Design, and Resource Planning. | Identify target schools, NGOs, orphanages, and the beneficiaries in the targeted age group. Finalize program timelines and roles, and responsibilities. Procure HPV vaccines from the selected vendor. |
| Phase 3: IEC material development. | Create culturally appropriate awareness content. Translate materials into regional languages. |
| Phase 4. Vaccination Rollout | Organize school based /community based/orphanage-based HPV vaccination drives. Maintained detailed records of the camps and girls vaccinated. Follow-up and second dose reminders to ensure full-dose completion. |
| Phase 5: Monitoring, Evaluation and Reporting | Reassess knowledge and vaccine coverage. Submit detailed financial and program reports to donors and other stakeholders. Document lessons learned for scale-up and/or replication. |

- Proposed Output/Outcome of the project:

Output- 1. No. of girls vaccinated (1st and 2nd doses). 2. No awareness sessions conducted and people reached. Outcome- 1. Increased awareness & acceptance of HPV vaccination among parents and adolescents. 2. Improved trust in the safety & importance of vaccines. 3. Functional delivery mechanism for school/community-based vaccinations.

- Monitoring and Evaluation Plan

| Sr. No | Objective | Key Indicators | Data Collection Method | Frequency |
| --- | --- | --- | --- | --- |
|  | Increased HPV vaccination coverage among girls aged 9-14 years. | # no. of girls who received 1st and 2nd dose of HPV vaccination | Vaccination registers. Camp attendance logs. | Bi-annually |
|  | M&E system for learning and scale-up. | Data reports submitted | Camp data analysis reports | Annually |

- Volunteer engagement plan (if applicable):

Volunteers can play a vital role in supporting the HPV Vaccination Program as part of their organization’s CSR engagement. Volunteers can participate in awareness sessions, help organize vaccination camps, and assist with logistics and beneficiary engagement. Volunteers can also contribute by designing IEC materials, managing data entry, or serving as vaccination day volunteers. Pre-engagement orientation will be provided to ensure they understand the program’s goals and sensitivity of the issue. Their involvement not only enhances program reach but also fosters a sense of social responsibility and purpose among employees, aligning corporate values with impactful community health outcomes.

- Budget Details

Total Proposed budget- 19,52,000

Budget Breakup-

| Budget Details |  |  |
| --- | --- | --- |
| Sr. No | Description | Total Cost (₹) |
| 1. | 2 Doses of Gardasil HPV Vaccination (200 girls) | 17,00,000 |
| 2. | Human resources (4 staff) | 64,000 |
| 3. | Miscellaneous (Printing/travel/vehicle) | 88,000 |
| 4. | Admin and Project implementation cost | 1,00,000 |
| Total Cost |  | ₹19,52,000 |